## Risk Register
MERIDIAN CONSULTING — INFORMATION SECURITY RISK REGISTER
50-Person Professional Services Firm ¦ Prepared: 2026-06-01 ¦ Next Review: 2026-12-01 ¦ Owner: IT Manager
Risk ID | Risk Name | Category | Description | Likelihood (1–5) | Impact (1–5) | Risk Score (L×I) | Risk Level | Current Controls | Response | Residual Risk Score | Residual Risk Level | Risk Owner | Review Date
R-001 | Ransomware via Phishing | Technology | Employee clicks malicious email link or attachment, deploying ransomware that encrypts M365, Salesforce data, and all 50 laptops. No offline backups exist. | 4 | 5 | 20 | Critical | M365 basic email filtering; no EDR, no security awareness training, no immutable backups | Mitigate | 8 | Medium | IT Manager | 2026-12-01
R-002 | Credential Theft / Account Takeover | Technology | Attacker compromises employee credentials via phishing or password spray, gaining access to M365, Salesforce, and financial data. No MFA enforced. | 4 | 4 | 16 | High | Minimum 8-char password policy; no MFA, no SIEM, no anomalous login alerting | Mitigate | 8 | Medium | IT Manager | 2026-12-01
R-003 | Sensitive Data Breach via Lost/Stolen Laptop | Technology | Unencrypted laptop containing client PII, contracts, or financial records is lost or stolen. 50 laptops, mix of personal and corporate devices. | 3 | 4 | 12 | High | No confirmed full-disk encryption policy; no MDM/device management enforced | Mitigate | 6 | Medium | IT Manager | 2026-09-01
R-004 | Insider Threat — Malicious Data Exfiltration | People | Disgruntled or departing employee exfiltrates client data, trade secrets, or financial records via personal email, USB, or cloud storage. | 2 | 5 | 10 | High | No DLP controls; no USB restrictions; offboarding checklist exists but not audited | Mitigate | 6 | Medium | HR Manager | 2026-12-01
R-005 | Third-Party / SaaS Vendor Breach | External | Salesforce, M365, or project management tool suffers a breach exposing Meridian client data. Company has no vendor security review process. | 3 | 4 | 12 | High | Vendor contractual SLAs only; no vendor risk assessments, no security questionnaires | Transfer | 9 | Medium | IT Manager | 2026-12-01
R-006 | Unpatched Software Vulnerabilities | Technology | Outdated OS or application vulnerabilities exploited on employee laptops. No centralized patch management with only 2 IT staff. | 3 | 3 | 9 | Medium | Manual patching; Windows Update enabled on most machines; no MDM enforcement | Mitigate | 4 | Low | IT Manager | 2026-09-01
R-007 | Business Email Compromise (BEC) | External | Attacker impersonates CEO or CFO via spoofed email to trick finance staff into fraudulent wire transfer. Common in $5-10M revenue firms. | 3 | 4 | 12 | High | M365 anti-spoofing (basic); no DMARC enforcement; no wire transfer approval process | Mitigate | 6 | Medium | CFO | 2026-12-01
R-008 | No Security Awareness Training | People | Employees unable to recognize phishing, social engineering, or data handling violations. Increases likelihood of nearly every other risk. | 4 | 3 | 12 | High | No formal training program; ad-hoc IT reminders only | Mitigate | 6 | Medium | IT Manager | 2026-09-01
R-009 | CCPA / State Privacy Law Non-Compliance | Process | Meridian processes California client PII without a compliant privacy policy, data inventory, or breach notification procedure. CCPA fines up to $7,500/record. | 3 | 4 | 12 | High | Basic privacy policy on website; no data inventory, no formal breach response plan | Mitigate | 8 | Medium | Legal / COO | 2026-09-01
R-010 | No Incident Response Plan | Process | No documented IR plan exists. In the event of ransomware, breach, or BEC, the team has no defined steps, contacts, or recovery procedures, extending downtime. | 4 | 4 | 16 | High | No IRP; IT manager handles incidents ad hoc; no cyber insurance confirmed | Mitigate | 8 | Medium | IT Manager / COO | 2026-09-01
R-011 | Shadow IT — Unauthorized Cloud App Usage | Process | Employees store client files in personal Dropbox, Google Drive, or other unapproved apps, bypassing M365 security controls and creating unmanaged data stores. | 4 | 2 | 8 | Medium | Acceptable Use Policy exists but not enforced; no CASB or cloud app monitoring | Accept | 6 | Medium | IT Manager | 2026-12-01
R-012 | Physical Security — Office Tailgating | External | Unauthorized individual gains physical access to office, accesses unlocked workstations, or steals hardware. Office in shared co-working building. | 2 | 3 | 6 | Medium | Keycard entry to suite; no camera system; clean desk policy not enforced | Accept | 3 | Low | Office Manager | 2026-12-01

## Risk Scoring Matrix
RISK SCORING MATRIX
Risk Score = Likelihood × Impact ¦ Scores: 1–4 = Low 5–9 = Medium 10–16 = High 17–25 = Critical
LIKELIHOOD ↓ | IMPACT →
| Impact 1 Minimal | Impact 2 Minor | Impact 3 Moderate | Impact 4 Severe | Impact 5 Catastrophic
Likelihood 5 Almost Certain | 5 | 10 | 15 | 20 | 25
Likelihood 4 Likely | 4 | 8 | 12 | 16 | 20
Likelihood 3 Possible | 3 | 6 | 9 | 12 | 15
Likelihood 2 Unlikely | 2 | 4 | 6 | 8 | 10
Likelihood 1 Rare | 1 | 2 | 3 | 4 | 5
LEGEND
1–4 | Low
5–9 | Medium
10–16 | High
17–25 | Critical

## Executive Summary
MERIDIAN CONSULTING — RISK REGISTER EXECUTIVE SUMMARY
Prepared: June 1, 2026 ¦ Prepared by: Security Analyst ¦ Review Cycle: Semi-Annual
RISK PORTFOLIO OVERVIEW
Critical Risks (Score 17–25) | 1
High Risks (Score 10–16) | 2
Medium Risks (Score 5–9) | 8
Low Risks (Score 1–4) | 1
Total Risks Identified | 12
TOP 3 PRIORITY RISKS
#1 — R-001: Ransomware via Phishing (Score: 20 — Critical)
Ransomware represents the highest risk to Meridian. With no EDR, no immutable backups, and no security awareness training, a single phishing click could encrypt all company and client data. Priority actions: (1) Deploy Microsoft Defender for Endpoint or equivalent EDR on all 50 laptops. (2) Implement M365 Backup or Azure Backup for immutable cloud backups. (3) Launch mandatory phishing awareness training immediately.
#2 — R-002: Credential Theft / Account Takeover (Score: 16 — High)
With no MFA enforced across M365 and Salesforce, a single compromised password grants full access to all company data and client records. This is the lowest-effort, highest-return attack for adversaries. Priority action: Enable MFA company-wide in M365 immediately — this is a one-day fix that eliminates 99% of account takeover risk.
#3 — R-010: No Incident Response Plan (Score: 16 — High)
Without a documented IR plan, any security incident — ransomware, breach, or BEC — will result in chaotic, slow response that extends downtime and increases regulatory exposure. Priority action: Draft a basic IR plan covering: (1) who to call, (2) how to contain, (3) how to notify clients and regulators. CCPA requires breach notification within 72 hours.
RECOMMENDED IMMEDIATE ACTIONS (QUICK WINS)
1. Enable MFA on M365 and Salesforce | Est. effort: 1 day ¦ Cost: Included in M365 license ¦ Eliminates ~99% of account takeover risk
2. Deploy EDR on all 50 laptops | Est. effort: 1 week ¦ Cost: ~$5-10/user/month ¦ Detects and stops ransomware execution
3. Launch security awareness training | Est. effort: 2 weeks setup ¦ Cost: ~$20-30/user/year ¦ Reduces phishing click rate by 70%+
4. Draft Incident Response Plan | Est. effort: 1 week ¦ Cost: Internal time only ¦ Required for CCPA breach notification compliance
5. Implement immutable M365 backup | Est. effort: 3 days ¦ Cost: ~$3/user/month ¦ Enables recovery from ransomware without paying ransom
6. Conduct data inventory / CCPA assessment | Est. effort: 2-4 weeks ¦ Cost: Internal + optional legal review ¦ Prevents $7,500/record CCPA fines